## Sheet1
Screen | Webapp | MobileApp | User/Admin |  |  |  | vendor | product
Country | Y |  | Admin |  |  |  | product | vendor
City | Y |  | Admin
Area | Y |  | Admin
Subscription | Y |  | Admin
Subscription percentage | Y |  | Admin | Done | 2023-01-07
Registration Type | Y |  | Database
SiteUsers | Y | Y | User/Admin | Done
Users |  |  |  | Done
Vendor to add product/Locations/Discount | Y | Y | User | Done | Apply cascade delete on vendor and vendor product
Product |  |  |  | Done
Addresses |  |  |  | Done | 29-06-2023
Home Screen with search | Y | Y | User/Admin
Login | Y | Y | User/Admin | Done
All refereals screens | Y | Y | User |  | getallReferrels | getallReferrelswithRegId | getreferrel | deleterefereal | Shazia
Wallet | Y | y | Admin/User |  | Getalltrnsactionsfromtransaction table |  |  |  | Mohtashim
Invitation screen | Y | Y | User |  | SendReferrallink using REgId with email, whatsapp,text |  |  |  | Mohtashim
Withdrawal/Balance transfer | Y | Y | Admin/User |  | aesy Paisa
Subscription Renewal | Y | Y | User | get , post
All payment screen (Transactions screen) | Y | Y | User | get transaction |  |  |  |  | Mohtashim
get transactions
posttransaction
deletetransaction
updatetransaction

## Sheet6
int | tranid
int | regId
float | amount
datetime | endate
string | enuser

## Sheet5
int | addid | int addid, | resource. | resource.addid, | Addid | address. | address.Addid,
int | regId | int regId, | resource. | resource.regId, | Regid | address. | address.Regid,
int | countryid | int countryid, | resource. | resource.countryid, | Countryid | address. | address.Countryid,
varchar(200) | cityid | varchar(200) cityid, | resource. | resource.cityid, | Cityid | address. | address.Cityid,
varchar(10) | streetaddress | varchar(10) streetaddress, | resource. | resource.streetaddress, | Streetaddress | address. | address.Streetaddress,
varchar(100) | postal | varchar(100) postal, | resource. | resource.postal, | Postal | address. | address.Postal,
varchar(100) | district | varchar(100) district, | resource. | resource.district, | District | address. | address.District,
varchar(100) | townstehsil | varchar(100) townstehsil, | resource. | resource.townstehsil, | Townstehsil | address. | address.Townstehsil,
varchar(100) | area | varchar(100) area, | resource. | resource.area, | Area | address. | address.Area,
varchar(100) | longitude | varchar(100) longitude, | resource. | resource.longitude, | Longitude | address. | address.Longitude,
| latitude | latitude, | resource. | resource.latitude, | Latitude | address. | address.Latitude,

## Sheet4
Productid | productid | = | resource. | productid=resource.productid | product. | product.Productid,
Catid | catid | = | resource. | catid=resource.catid | product. | product.Catid,
Productname | productname | = | resource. | productname=resource.productname | product. | product.Productname,
Productcode | productcode | = | resource. | productcode=resource.productcode | product. | product.Productcode,
Picture | picture | = | resource. | picture=resource.picture | product. | product.Picture,
Discountpercentage | discountpercentage | = | resource. | discountpercentage=resource.discountpercentage | product. | product.Discountpercentage,
Discountamount | discountamount | = | resource. | discountamount=resource.discountamount | product. | product.Discountamount,
Discountcode | discountcode | = | resource. | discountcode=resource.discountcode | product. | product.Discountcode,
Dicountcondition | dicountcondition | = | resource. | dicountcondition=resource.dicountcondition | product. | product.Dicountcondition,

## Timelines
Task |  | Start | End | Days
Structure | Started | 10th Jun | 15th Jun
Backend Web API |  | 16th Jun | 26th Jun
Mobile App |  | 25th Jun | 10th July
Users |  |  |  | 2
Vendor to add product/Locations/Discount |  |  |  | 2
Home Screen with search |  |  |  | 3
Login
All referrals screens |  |  |  | 1
Wallet |  |  |  | 2
Invitation screen |  |  |  | 1
Withdrawal/Balance transfer |  |  |  | 0
All payment screen (Transactions screen) |  |  |  | 1
WebApp |  | 27th Jun | 15th July
Country |  |  |  | 1
City |  |  |  | 1
Area |  |  |  | 1
Subscription |  |  |  | 1
Subscription percentage |  |  |  | 1
Registration Type |  |  |  | 1
Registration |  |  |  | 3
Vendor to add product/Locations/Discount |  |  |  | 3
Home Screen with search |  |  |  | 3
Login |  |  |  | 0
All refereals screens |  |  |  | 1
Wallet |  |  |  | 2 | Easy paisa API needs to be tested
Invitation screen |  |  |  | 2 | link and whatsapp, email
Withdrawal/Balance transfer |  |  |  | 1
Subscription Renewal |  |  |  | 1
All payment screen (Transactions screen) |  |  |  | 2

## Sheet3
Task |  | Start | End | Days
Structure | Completed | 10th Jun | 15th Jun
Backend Web API |  | 16th Jun | 26th Jun
Mobile App |  | 25th Jun | 15th July
WebApp |  | 27th Jun | 20th July
Testing |  | 21st Jul | 30th July

## Sheet2
Working on Siteuser API
End points
| Password encryption | Done
| JWT | Done

## API
Entities | APIs | Parameter | Start Date | End Date
SiteUsers | Register, Login |  | 2023-06-20 | 2023-06-21
Users | Register, Login |  | 2023-06-20 | 2023-06-21
| GetUsers |  | 2023-06-22 | 2023-06-22
| DeleteUser | ID | 2023-06-22 | 2023-06-22
| GetUserID | ID | 2023-06-22 | 2023-06-22
| UpdateUser | ID | 2023-06-22 | 2023-06-22
JWT Token |  |  | 2023-06-21 | 2023-06-22
Country | GetCountries |  | 2023-06-22 | 2023-06-22
| GetCoutryID | ID | 2023-06-22 | 2023-06-22
| DeleteCoutryID | ID | 2023-06-22 | 2023-06-22
| UpdateCountryID | ID | 2023-06-22 | 2023-06-22
City | GetCountries |  | 2023-06-22 | 2023-06-22
| GetCoutryID | ID | 2023-06-22 | 2023-06-22
| DeleteCoutryID | ID | 2023-06-22 | 2023-06-22
| UpdateCountryID | ID | 2023-06-22 | 2023-06-22
Area | GetCities |  | 2023-06-22 | 2023-06-22
| GetCityID | ID | 2023-06-22 | 2023-06-22
| DeleteCityID | ID | 2023-06-22 | 2023-06-22
| UpdateCityID | ID | 2023-06-22 | 2023-06-22